## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | Set up basic IVR call flow and DTMF handling | MUST HAVE | None | Team B (10 members) | 3- Completed
Sprint 1 | Sprint 1 | US02 | Configure backend APIs for IVR responses | MUST HAVE | US01 | Team B (10 members) | 3- Completed
Sprint 2 | Sprint 2 | US03 | Integrate AI-based speech recognition | SHOULD HAVE | US02 | Team B (10 members) | 3- Completed
Sprint 2 | Sprint 2 | US04 | Connect speech output to IVR prompts | SHOULD HAVE | US03 | Team B (10 members) | 3- Completed
Sprint 3 | Sprint 3 | US05 | Implement Conversational AI integration (NLU) | MUST HAVE | US04 | Team B (10 members) | 3- Completed
Sprint 3 | Sprint 3 | US06 | Enable intent mapping and dialogue flow | MUST HAVE | US05 | Team B (10 members) | 3- Completed
Sprint 4 | Sprint 4 | US07 | Develop centralized error handling & validation | COULD HAVE | None | Team B (10 members) | 3- Completed
Sprint 4 | Sprint 4 | US08 | Create final documentation and presentation | MUST HAVE | All previous | Team B (10 members) | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Create IVR call flow using VXML | 2025-09-02 | 2025-09-05 | Team B (10 Members) | Development | 3- Completed
US02 | T02 | Build backend API endpoints | 2025-09-05 | 2025-09-09 | Team B (10 Members) | Development | 3- Completed
US03 | T03 | Integrate STT (Speech-to-Text) module | 2025-09-10 | 2025-09-13 | Team B (10 Members) | Integration | 3- Completed
US05 | T04 | Implement NLU with Dialogflow | 2025-09-15 | 2025-09-18 | Team B (10 Members) | AI Integration | 3- Completed
US06 | T05 | Create IVR call flow using VXML | 2025-09-18 | 2025-09-20 | Team B (10 Members) | Testing | 3- Completed
US07 | T06 | Implement error handling middleware | 2025-09-22 | 2025-09-24 | Team B (10 Members) | Development | 3- Completed
US08 | T07 | Prepare documentation and final PPT | 2025-09-25 | 2025-09-27 | Team B (10 Members) | Documentation | 3- Completed
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty in connecting API to VXML | Debugged endpoint and updated routing
Sprint 2 | Day 3 | Speech recognition accuracy was low | Improved model confidence threshold
Sprint 3 | Day 4 | Delay in Dialogflow API integration | Rescheduled tasks and pair-programmed
Sprint 4 | Day 5 | Error validation conflicts | Implemented centralized error middleware

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-02 | 2025-09-09 | Team B (10 Members) | Maintain consistent Git commits | Rushing testing | Collaborative coding | Added peer code reviews
2 | Sprint 2 | 2025-09-10 | 2025-09-15 | Team B (10 Members) | Proper documentation | Late-night pushes | Daily progress updates | Weekly report submission
3 | Sprint 3 | 2025-09-16 | 2025-09-22 | Team B (10 Members) | Clear role division | Overlapping tasks | Cross-verification | Introduced task allocation chart
4 | Sprint 4 | 2025-09-23 | 2025-09-30 | Team B (10 Members) | Mock presentation before final | Unplanned code changes | Continuous improvement | Prepared final demo checklist